## Dashboard
Ameya Heights — Roadmap Progress
Live. Every figure is a formula over the Roadmap tab; it updates as you change Status.
TOTAL ACTIONS |  | DONE |  | IN PROGRESS |  | P1 OUTSTANDING
COMPLETION |  | EFFORT REMAINING (HOURS) |  | EFFORT DONE (HOURS) |  | BLOCKED
BY HORIZON
Horizon | Total | Done | Remaining | Hours left | % done
Done · v13
H1 · Stabilise
H2 · Instrument
H3 · Compound
BY WORKSTREAM
Workstream | Total | Done | Hours left
AI
AI continuity
Accessibility
Analytics
Channels
Code quality
Compliance
Content
Deploy
Engineering
Growth
Hygiene
Ops
Performance
Resilience
SEO
Sales
Security

## Roadmap
Ameya Heights — Digital Roadmap Tracker
Execution tracker for the enterprise audit. Change only the yellow columns (Status, Owner, Target date, Notes) — everything else recalculates.
ID | Horizon | Workstream | Action | Why it matters | Owner | Effort (h) | Priority | Status | Blocked by | Target date | Notes
A1 | Done · v13 | Hygiene | Delete 7 scratch HTML files from the deploy root | Draft files were publicly reachable, not in sitemap, no noindex | Claude | 0.2 | P1 | Done
A2 | Done · v13 | Hygiene | Add Disallow rules to robots.txt (/_ , /api/, widget) | Belt-and-braces against crawling internal fragments | Claude | 0.1 | P2 | Done
A3 | Done · v13 | Performance | Move 3 legal modals to on-demand /legal-modals.html | Removed 860 KB of duplicated markup; homepage HTML -38% | Claude | 2 | P1 | Done
A4 | Done · v13 | Performance | Lazy-load 26 non-hero images; 1 eager hero per page | Frees bandwidth for the LCP element on mobile | Claude | 1 | P1 | Done
A5 | Done · v13 | Performance | Add intrinsic width/height to images missing them | Prevents cumulative layout shift | Claude | 0.5 | P2 | Done
A6 | Done · v13 | Performance | Generate responsive variants + srcset for 5 heavy images | Phones stop downloading 1600px imagery | Claude | 1.5 | P1 | Done
A7 | Done · v13 | Analytics | Build track.js and wire all 8 conversion events | You could not previously see which tool produces leads | Claude | 3 | P1 | Done
A8 | Done · v13 | SEO | Trim 7 pages' titles/descriptions into best-practice range | All 30 indexable pages now compliant | Claude | 1 | P2 | Done
A9 | Done · v13 | Resilience | Lead rescue path: retry + email/webhook on sheet failure | A failed sheet write no longer silently loses the enquiry | Claude | 2 | P1 | Done
A10 | Done · v13 | Code quality | Replace raw control bytes in security.js with escapes | Invisible characters in source can be mangled by any tool | Claude | 0.3 | P3 | Done
A11 | Done · v13 | Ops | Write the operations runbook | Removes key-person dependency during an incident | Claude | 2 | P1 | Done
B1 | H1 · Stabilise | AI continuity | Move off free Gemini quota, or add a failover key | TOP RISK. Concierge dies at peak enquiry hours; already seen in production | You | 1 | P1 | In progress | two distinct models live; still one provider + one key
B2 | H1 · Stabilise | Ops | Add uptime monitoring on / and /api/health | Today you learn the site is down from a customer | You | 1 | P1 | In progress | /api/monitor live + daily cron; add cron-job.org for 5-min checks
B3 | H1 · Stabilise | Ops | Add browser error tracking (Sentry free tier) | JavaScript errors in real browsers are currently invisible | You | 1.5 | P1 | Done | report_endpoint:true; alert email received
B4 | H1 · Stabilise | Resilience | Set ALERT_EMAIL_TO + RESCUE_WEBHOOK_URL in Vercel | Activates the rescue path built in A9 — it is inert without these | You | 0.3 | P1 | Done | routed via Apps Script relay; testAlerts confirmed
B5 | H1 · Stabilise | Deploy | Deploy build v13 and verify the ?v= bumps took effect | Stale CDN copies are invisible failures | You | 0.5 | P1 | Done | v18 live; verified by asset probe
B6 | H1 · Stabilise | AI | Turn on the chat log endpoint | You cannot improve what you cannot see | You | 0.5 | P1 | Done | chat_log_endpoint:true confirmed live
B7 | H1 · Stabilise | Ops | Run checkSender + sendTestEmail, publish a New Version | Apps Script edits do not go live until a new version is published | You | 0.5 | P1 | Not started
B8 | H1 · Stabilise | Analytics | Create the 8 events as GA4 conversions in GTM | Events fire but are not yet registered as conversions | You | 1 | P2 | Not started | A7
C1 | H2 · Instrument | Performance | Run PageSpeed Insights; record real Core Web Vitals | Replaces my projection with measured field data | You | 0.5 | P1 | Done | mobile 71 / desktop 93; LCP 5.3s mobile
C2 | H2 · Instrument | SEO | Pull Search Console impressions, position, coverage | Establishes the organic baseline this audit could not verify | You | 1 | P1 | Not started
C3 | H2 · Instrument | SEO | Check referring domains (Ahrefs free authority checker) | Authority, not markup, is your binding SEO constraint | You | 0.5 | P1 | Not started
C4 | H2 · Instrument | AI | Review chat transcripts weekly; log recurring questions | Buyer questions are free market research | You | 1 | P2 | Not started | B6
C5 | H2 · Instrument | Accessibility | axe DevTools pass + manual screen-reader check | Automated layer is clean; lets you claim WCAG 2.1 AA with confidence | You | 3 | P2 | In progress | Skip links 46/46 done; manual screen-reader pass still open
C6 | H2 · Instrument | Compliance | Have an Indian privacy practitioner review DPDPA consent | Itemised notice + documented erasure process are required | Counsel | 4 | P1 | Not started
C7 | H2 · Instrument | Resilience | Weekly automated backup of the Leads sheet | Currently Google durability only; no independent copy | You | 1.5 | P2 | In progress | IDs filled in; run backupLeads() once + add the weekly trigger
C8 | H2 · Instrument | Performance | Convert remaining legacy JPG/PNG files to WebP | Typically 25-35% smaller at equal quality | You | 2 | P3 | Done | 4 of 7 converted; 3 refused (WebP was larger)
D1 | H3 · Compound | Engineering | Minimal build step with content-hashed asset filenames | Permanently ends the manual ?v= fragility | Dev | 8 | P2 | Done | stamp-assets.mjs + build.py path bug fixed
D2 | H3 · Compound | Engineering | Smoke tests on Vercel preview deploys | Nothing currently stops a broken deploy reaching production | Dev | 8 | P2 | Done | 36 tests passing, desktop + mobile
D3 | H3 · Compound | Channels | Activate WhatsApp Business API (scaffolding already built) | Where Indian buyers actually converse; same brain | You | 6 | P2 | Not started | Scaffolding built; needs Meta credentials
D4 | H3 · Compound | Growth | Portal listings + digital PR: first 20 referring domains | The single biggest lever on organic visibility | You | 20 | P1 | In progress | Authority plan delivered; outreach is yours
D5 | H3 · Compound | Content | Publish pages answering the top chat questions | Content that earns links because it answers real demand | You | 12 | P2 | Not started | C4
D6 | H3 · Compound | Sales | Staff the human handoff console | Routing exists; nobody is behind it | You | 4 | P2 | Not started
D7 | H3 · Compound | Security | Migrate CSP from 'unsafe-inline' to nonce-based | Closes the last real softness in an otherwise strong policy | Dev | 6 | P2 | Not started | D1
D8 | H3 · Compound | Ops | Dependency scanning (Dependabot / npm audit in CI) | Vulnerable libraries currently go unnoticed | Dev | 2 | P3 | Done | CI audit job + Dependabot

## Scorecard
Audit Scorecard — current vs. target
Current scores are from the July 2026 audit. Target is what closing the roadmap should achieve. Update 'Current' after you re-audit.
Category | Weight % | Current | Target | Gap | What closes the gap
Innovation & differentiation | 4% | 93 | 95 |  | Already category-leading; maintain
AI readiness | 10% | 93 | 96 |  | Paid quota / failover ends the fragility (B1)
SEO & discoverability | 10% | 90 | 93 |  | Authority work: referring domains (D4)
Security posture | 12% | 86 | 93 |  | Nonce-based CSP (D7); DPDPA review (C6)
UX & accessibility | 8% | 88 | 92 |  | Manual a11y pass + skip links (C5)
Website health | 8% | 92 | 95 |  | CORRECTED: a CI gate was already present; 36 tests now green
Scalability & cost | 6% | 83 | 88 |  | AI quota is the only real ceiling (B1)
Conversion architecture | 10% | 80 | 88 |  | Events now firing (A7); register conversions (B8)
Technology maturity | 10% | 90 | 93 |  | CORRECTED: build.py, CI and tests already existed; audit understated this
Performance | 10% | 75 | 86 |  | Legal modals + lazy-load done; measure real CWV (C1)
Data & analytics | 4% | 82 | 88 |  | Search Console + chat logs (C2, B6)
Enterprise readiness | 8% | 78 | 88 |  | Monitoring, runbook, backups (B2, B3, A11, C7)
COMPOSITE (weighted)

## How to use
How to use this tracker
YELLOW CELLS ARE YOURS |  | Edit only these. Everything else is a formula and will recalculate.
Roadmap!F (Owner) | edit | Who is actually doing it.
Roadmap!I (Status) | edit | Pick from the dropdown: Not started / In progress / Blocked / Done / Dropped.
Roadmap!K (Target date) | edit | Your committed date.
Roadmap!L (Notes) | edit | Anything worth remembering.
Scorecard!C (Current) | edit | Update after you re-audit.
READ-ONLY
Dashboard | formula | Recalculates from Roadmap. Do not type over it.
Roadmap!G (Effort) | estimate | Hours. Rough, but consistent across rows.
Roadmap!J (Blocked by) | reference | The ID that must finish first.
PRIORITIES
P1 |  | Do first. Directly protects revenue or continuity.
P2 |  | Important, not urgent. Compounding value.
P3 |  | Housekeeping. Do when convenient.
A NOTE ON THE 'Done · v13' ROWS |  | Those eleven actions were completed and verified in the build delivered with this tracker. They are listed so the record is complete and so the effort figures mean something — not as work still to schedule.
WHAT THIS TRACKER CANNOT TELL YOU |  | Traffic, rankings, backlinks and real Core Web Vitals are not in here because they were never measured. Actions C1, C2 and C3 exist specifically to go and get those numbers. Until then, treat any performance or SEO figure in the audit as a projection.